## Introduction
Project Name
What is this? | This workbook is meant to help manage and piroritize the user stories and features using scrum.
How to use and read this document? | Before project start: The product owner is responsible for managing and maintaining the product backlog of user stories.
Before each sprint: The vendor will break down the user stories into tasks.
Notes | Cells that you can edit have a blue background.
Sprints are assumed to be 2 weeks long (10 working days)/
Licence | This work is licensed under a Creative Commons Attribution-Share Alike 3.0 Unported License.
Origins | This work is inspired by the Scrum Template published by Nicolas Martignole on his "Touilleur Express" blog. Adapted by Olivier Gérardin.

## Product Backlog
Book Management System
| Organizations | Backend Development Team Backend & Database Team Backend & Frontend Team Frontend & Backend Team Database Team Security Team Frontend Development Team QA & Testing Team
| Project | Bookstore Management System
| Product Owner | Cody Peterson / Johnathan Kavanaugh
| Scrum Master | Lary Hezekiah
| Development Team | Latherio Kidd
Story ID | Title | Description | Acceptance Criteria | Priority # | Sprint # | Responsibility
S1-001 | User Authentication & Role-Based Access | As a bookstore staff member, I want to log in securely so that I can access system features based on my role. | Successful login with valid credentials; Unauthorized users restricted; Multi-factor authentication enabled. | High | Sprint 1 | Backend Development Team
S1-002 | Inventory Management - Book Tracking | As a store manager, I want to track books from entry to sale so that inventory is always accurate. | Books can be added, edited, removed; Inventory updates in real-time; Low-stock alerts generated. | High | Sprint 1 | Backend & Database Team
S1-003 | Sales Processing - Point of Sale (POS) | As a cashier, I want to process transactions so that customers can complete their purchases quickly. | Sales recorded with timestamps; Payment integration works; Receipts generated. | High | Sprint 1 | Backend & Frontend Team
S1-004 | Customer Order Management - Cart & Checkout | As a customer, I want to add books to a cart and check out so that I can complete my purchase online. | Users can add/remove items from cart; Orders are confirmed via email; Payment is processed securely. | Medium | Sprint 1 | Frontend & Backend Team
S1-005 | Database Setup & Optimization | As a developer, I want a well-structured relational database so that all system data is stored efficiently. | Database schema designed; Relationships between tables defined; Optimized for fast queries. | High | Sprint 1 | Database Team
S1-006 | Security & Compliance Measures | As a security analyst, I want the system to be secure so that customer and business data is protected. | Passwords encrypted; PCI-compliant payment processing; Audit logs implemented. | High | Sprint 1 | Security Team
S1-007 | User Interface (UI) Design - Admin & Customer Dashboards | As a UI designer, I want a responsive interface so that users can navigate the system easily. | Admin panel designed; Customer dashboard functional; Mobile responsiveness ensured. | Medium | Sprint 1 | Frontend Development Team
S1-008 | Testing & Quality Assurance | As a QA engineer, I want to conduct rigorous testing so that system functionalities work as expected. | Unit tests cover 90%+ of code; Integration tests for key features; User acceptance testing completed. | High | Sprint 1 | QA & Testing Team
S1-009 | User Authentication - Multi-Factor Authentication | As a security analyst, I want multi-factor authentication (MFA) enabled so that unauthorized access is prevented. | Users must verify via OTP or authenticator app; MFA required for admin logins; Option to enable/disable MFA in settings. | High | Sprint 1 | Security Team
S1-010 | Inventory Management - Barcode Scanning | As a store manager, I want barcode scanning enabled so that book inventory updates are faster and more accurate. | Barcode scanner integrates with inventory system; ISBN lookup auto-fills book details; Supports manual entry fallback. | High | Sprint 1 | Backend & Frontend Team
S1-011 | Sales System - Discount & Promotions | As a cashier, I want a discount system so that I can apply promotions to customer purchases. | Cashiers can apply discounts during checkout; System auto-applies valid promotions; Discounted total displayed before payment. | Medium | Sprint 1 | Backend & Frontend Team
S2-001 | Sales Processing (POS) | Process transactions with timestamps & receipts | Sales recorded with timestamps, receipt generation validated | High | Sprint 2 | Backend & Frontend
S2-002 | Cart & Checkout | Add/remove items, order confirmation, secure checkout | Secure checkout, confirmed orders, UI/backend integration | High | Sprint 2 | Frontend & Backend
S2-003 | Add test inventory & Optimize DB | Optimize DB queries, validate relational integrity | Optimized queries, validated data relationships, performance metrics | High | Sprint 2 | Backend
S2-004 | Security & Compliance Measures | Encrypt passwords, implement audit logs, ensure PCI compliance | Password encryption, audit logs verified, PCI checks complete | High | Sprint 2 | Security & Compliance
S2-005 | UI Design - Admin & Customer Dashboards | Ensure responsive UI for admin/customer | Responsive UI; dashboard links functional | Medium | Sprint 2 | Frontend
S2-006 | Testing & Quality Assurance | Unit test coverage >90%, integration, UAT | Unit tests completed, passed UAT scenarios | High | Sprint 2 | QA & Testing (Scrum Master, Kidd, Peterson)
S2-007 | Multi-Factor Authentication (MFA) | Enable MFA toggle and OTP support | OTP/Authenticator option, toggle interface built | High | Sprint 2 | Security (Kidd), Product Owner (Peterson)
S2-008 | Inventory Mgmt - Barcode Scanning | Barcode scanner integration with inventory system | Scanner fetches book details, fallback supported | Medium | Sprint 2 | Backend & Database
S3-001 | Sales System - Discounts & Promotions | Apply discounts, auto-validate promotions | Discounts apply at checkout; displayed correctly | Medium | Sprint 3 | Backend & Frontend

## Sprint 1
Sprint #1Tracking Sheet
|  | Project |  | Book Management
|  | Sprint # |  | 1
|  | Start date |  | 2025-03-25
|  |  | Total Team Members | 4
[5 empty] | week 1 | [6 empty] | week 2 | [6 empty] | Overage per Task (Hours)
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Task ID | Story ID | Description | Responsibility | Initial estimate | 2025-03-25 | 2025-03-26 | 2025-03-27 | 2025-03-28 | 2025-03-29 | 2025-03-30 | 2025-03-31 | 2025-04-01 | 2025-04-02 | 2025-04-03 | 2025-04-04 | 2025-04-05 | 2025-04-06 | 2025-04-07
1 | NF-001 | Sprint Planning Meeting | Scrum Master (Larry Hezekiah) & Latherio Kidd) | 2 | 2025-03-27: 2 | 0
2 | NF-002 | Infrastructure Setup (Backend, Database) | Backend & DevOps (Latherio Kidd) | 8 | 2025-03-28: 6; 2025-03-29: 9.5 | 7.5
3 | NF-003 | Daily Standup Meetings | Scrum Master (Larry Hezekiah) & All Members | 5 | [14 empty] | -5
4 | NF-004 | Code Reviews & Internal Testing | Latherio Kidd & Johnathan Kavanaugh | 6 | [14 empty] | -6
5 | NF-005 | Sprint Review | Scrum Master (Larry Hezekiah) & All Members | 2 | [14 empty] | -2
6 | NF-006 | Sprint Retrospective | Scrum Master (Larry Hezekiah) & All Members | 2 | [14 empty] | -2
7 | S1-001 | Develop user authentication & role-based access control | Backend (Latherio Kidd) | 16 | 2025-03-30: 6; 2025-04-02: 2; 2025-04-03: 5; 2025-04-04: 2; 2025-04-05: 4 | 3
8 | S1-002 | Implement inventory management system for book tracking | Backend & Database (Latherio Kidd) | 20 | 2025-03-30: 6; 2025-04-01: 4; 2025-04-02: 2; 2025-04-03: 7; 2025-04-04: 2; 2025-04-05: 4 | 5
9 | S1-003 | Design wireframes for Login, Inventory, Book Edit views | Front-End (Johnathan Kavanaugh & Latherio Kidd) | 6 | 2025-03-28: 3 | -3
10 | S1-004 | Develop HTML/CSS layout for core views | Front-End (Latherio Kidd) | 8 | 2025-04-06: 5 | -3
11 | S1-005 | Draft user stories and acceptance criteria (e.g. inventory CRUD) | Product Owner (Cody Peterson) | 4 | 2025-03-29: 1; 2025-04-06: 3 | 0
12 | S1-006 | Define system variable conventions and naming standards | Product Owner (Cody Peterson) | 3 | 2025-03-28: 2 | -1
|  | Remaining units (actual) |  | 64 | #N/A | #N/A | 62 | 51 | 40.5 | 28.5 | #N/A | 24.5 | 20.5 | 8.5 | 4.5 | -3.5 | -11.5 | #N/A | -6.5
|  | Remaining units (ideal) |  |  | 59.4286 | 54.8571 | 50.2857 | 45.7143 | 41.1429 | 36.5714 | 32 | 27.4286 | 22.8571 | 18.2857 | 13.7143 | 9.1429 | 4.5714 | 2.1316e-14
[10 empty] | 0 | 82 | [5 empty] | 0 | 0
[10 empty] | 10 | 0 | [5 empty] | 10 | 0

## Sprint 2
Sprint #2Tracking Sheet
|  | Project |  | Bookstore Management System
|  | Sprint # |  | 2
|  | Start date |  | 2025-04-07
|  |  | Total Team Members | 4
[5 empty] | week 1 | [6 empty] | week 2 | [6 empty] | Overage per Task (Hours)
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Task ID | Story ID | Description | Responsibility | Initial estimate | 2025-04-07 | 2025-04-08 | 2025-04-09 | 2025-04-10 | 2025-04-11 | 2025-04-12 | 2025-04-13 | 2025-04-14 | 2025-04-15 | 2025-04-16 | 2025-04-17 | 2025-04-18 | 2025-04-19 | 2025-04-20
9 | S2-001 | Develop sales processing & POS integration | Backend & Frontend (Latherio Kidd) | 10 | [14 empty] | -10
10 | S2-002 | Implement customer order management (Cart & Checkout) | Frontend & Backend (Latherio Kidd) | 10 | [14 empty] | -10
11 | S2-003 | Set up and optimize the database | Database (Latherio Kidd) | 6 | [14 empty] | -6
12 | S2-004 | Implement security & compliance measures | Security & Compliance (Latherio Kidd & John Kavanaugh) | 5 | [14 empty] | -5
13 | S2-005 | Design and develop UI for admin & customer dashboards | Frontend (Latherio Kidd) | 8 | [14 empty] | -8
14 | S2-006 | Conduct testing & quality assurance | QA (Scrum Master) & Testing (Latherio Kidd, John Kavanaugh, & Cody Peterson) | 6 | [14 empty] | -6
15 | S2-007 | Enable multi-factor authentication (MFA) | Security (Latherio Kidd) & Product Owner (Cody Peterson) | 4 | [14 empty] | -4
16 | S2-008 | Integrate barcode scanning for inventory management | Backend & Database (Latherio Kidd) | 6 | [14 empty] | -6
17 | S2-009 | Refine Backlog and acceptance crititeria for new features | Product Owner (Cody Peterson & John Kavanaugh) | 3 | [14 empty] | -3
18 | S2-010 | Review UI/ UX for usability and consistency | Product Owner (Cody Peterson & John Kavanaugh) | 3 | [14 empty] | -3
|  | Remaining units (actual) |  | 64 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | -61
|  | Remaining units (ideal) |  |  | 59.4286 | 54.8571 | 50.2857 | 45.7143 | 41.1429 | 36.5714 | 32 | 27.4286 | 22.8571 | 18.2857 | 13.7143 | 9.1429 | 4.5714 | 2.1316e-14
[10 empty] | 0 | 61 | [5 empty] | 0 | 0
[10 empty] | 10 | 0 | [5 empty] | 10 | 0